## Instructions
Risk Assessment Worksheet: System Selection
2015 Version (v1.03)
Published by Axia Consulting Ltd, 17 New Road Avenue, Chatham, Kent ME4 6BA, United Kingdom.
Web: www.axia-consulting.co.uk Email: info@axia-consulting.co.uk
Axia Consulting Ltd gives no warranty (either expressed or implied) in relation to the quality, accuracy, performance and fitness for purpose of this Risk Assessment Worksheet. Axia Consulting Ltd will not be liable for any loss or damage (whether directly or indirectly suffered), or any consequential loss arising from the use of this Risk Assessment Worksheet.
Copyright © 2015 Axia Consulting Ltd. All rights reserved.
This ‘Risk Assessment Worksheet’ is free for personal use and to help you with projects internally within your organisation. However, you are not permitted to display this ‘Risk Assessment Worksheet’ on the Internet, whether in part or whole, whether modified or not, nor to advertise, resell or obtain a commercial benefit from it.
Worksheet objectives:
1: to quickly identify potential risks within a software system selection process - a 100 potential risks are listed which you may amend as appropriate for your system selection process
2: to evaluate the risks by scoring their potential impact and probability of occurrence
3: to identify and list responses (strategy, recommendations, actions) to manage the risks
NB: risks should be regularly reviewed as they may change during the course of the system selection process.
INSTRUCTIONS are below (click the tab at the bottom of the screen to access the Risk Assessment Worksheet)
Column A (Ref) - risk reference. Leave the reference numbers as they are or amend as required.
Column B (Risk definition - cause) - review, amend, add to or delete as required, to tailor to your specific situation.
Column C (Risk definition - impact) - review, amend, add to or delete as required, to tailor to your specific situation.
Column D (Impact score) - for evaluating the potential impact of a risk. An easy-to-use numerical weighting range is listed below, but other ranges can be used. The default is 1 (the lowest impact). Change as appropriate.
- range from 1 to 10, where 1 = the lowest impact and 10 = the largest possible impact
Column E (Prob) - for probability of the risk occurring. An easy-to-use numerical scoring range is listed below, but other ranges can be used. The default is 0.1 (the lowest probability). Change as appropriate.
- range from 0.1 to 0.9, where 0.1 = the lowest probability and 0.9 = the highest probability
- NB: cannot use 0.0 - as the risk would never happen, or 1 as the risk would be certain to happen.
Column F (Wt Score) - for weighted score. Automatically calculated (Impact Score x Probability = Wt Score). The results show where your greatest risks are, ie those risks with the highest scores. And low risks will have low scores. Average weighted scores (automatically calculated) give an indication of which areas to look at to identify the greatest risks.
Column G (Risk response strategy) - for your strategy in responding to each specific risk. Focus attention on those risks with the highest weighted scores first. An easy-to-use list of risk reponse strategies is below, but these may be amended. The default is "chose strategy". Click each cell, then tab to change as appropriate.
- Avoid risk eg changing or doing something to take away the risk
- Transfer risk eg transferring the risk to another organisation / somebody else
- Mitigate risk eg taking actions to reduce the impact or probability of the risk
- Accept risk eg doing nothing as the risk is either too small, or the costs of any actions outweigh the costs of the risk
If you wish amend the risk response strategy terms, the instructions are:
1. Amend your ‘strategy’ terms in the Risk Assessment Worksheet cells G179-G183 – or extend the range for more terms.
2. Click cell G25 (or any other ‘risk response strategy’ cell)
3. Then select the ‘Data’ tab - then in Data Tools, select ’Data Validation’- then Settings and check that the Source is: =$G$179:$G$183 or whatever the range is for your different strategy terms. Then click ‘OK’
4. Then click cell G25 scroll tab to test out your different risk response strategy options.
5. If they are correct, then copy and paste to the other ‘risk response strategy’ cells.
Column H (Risk response recommendations) - for you to list / detail your recommendations in dealing with the risk and applying the chosen strategy. Insert additional rows (in the worksheet) for additional recommendations.
Column I (Risk response actions) - for you to list / detail your actions to achieve the recommendations. Insert additional rows (in the worksheet) for additional actions.
Column J (By) - for the name / details of who is responsible for carrying out the action(s).
Column K (Due date) - for the action to be completed.
Column L (Complete date) - when the action has been completed.
The worksheet is completely flexible. Rows and columns may be resized. Data may be amended. Additional worksheets may be added.
All calculated figures are in coloured in orange, to assist easy recognition, however, the colour may be changed as desired. The worksheet uses simple Excel calculations (addition, multiplication etc) to calculate weighted scores, average weighted scores. No macros are used. Calculations may be altered as required. After changes have been made to the worksheet, it is recommended that the calculations are checked.
Further information about software selection may be found at:
http://www.axia-consulting.co.uk/html/resources.html

## Risk Assessment Worksheet
Risk Assessment Worksheet: System Selection
Project name:
|  |  | Impact |  | Wt | Risk Response | Risk Response | Risk Response |  | Due | Complete
Ref | Risk definition - cause | Risk definition - impact | Score | Prob | Score | Strategy | Recommendations | Actions | By | Date | Date
Summary / Average Weighted Scores
1 | Selection methodology |  |  |  | 0.1
2 | Business objectives |  |  |  | 0.95
3 | Business case |  |  |  | 1.1933
4 | Executive support |  |  |  | 0.31429
5 | Scope |  |  |  | 0.4875
6 | Business / project requirements |  |  |  | 0.5625
7 | User involvement |  |  |  | 0.47857
8 | Project manager and IT support |  |  |  | 0.6
9 | Software system infrastructure |  |  |  | 0.53333
10 | Project management of the system selection |  |  |  | 0.1
11 | Vendor and software system information |  |  |  | 0.1
| Total weighted average score |  |  |  | 0.49268
1 | Selection methodology
1.1 | No formal system selection process methodology used | Not all aspects of the selection process may be covered, issues may be missed, increased difficulty in selecting the most appropriate vendor / software system | 1 | 0.1 | 0.1 | Chose strategy
1.2 | Not treating the system selection process as a discrete (small) project | Selection process may not be adequately controlled, process may take longer, mistakes may be made | 1 | 0.1 | 0.1 | Chose strategy
1.3 | No or a vague 'project charter' or 'terms of reference' | No or confusing statement of project scope, objectives, project reference of authority and initial delineation of people involved, responsibilities, authorities | 1 | 0.1 | 0.1 | Chose strategy
1.4 | No project steering group or one that only meets occasionally, with limited participation | Limited monitoring of the project progress and budget, limited advice on project issues / direction, limited communication and dissemination of information | 1 | 0.1 | 0.1 | Chose strategy
1.5 | No dedicated project team (of users, IT and a project manager) set up, or only partly set up (with a loose collection of individuals requested to work on certain tasks) | Unclear responsibilities, project related tasks not accepted, leading to potential conflicts, confusion and the project slowing down | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 0.1
2 | Business objectives
2.1 | Unclear or no business objectives and vision for the project | Continuing questions about what the project is for, what it is to achieve, its objectives / benefits | 3 | 0.3 | 0.9 | Avoid risk
2.2 | Business objectives / vision not agreed by users and management / executives | Potential disagreements and conflict, slowing the project down until resolved / agreed | 5 | 0.2 | 1 | Avoid risk
|  | Average Weighted Score |  |  | 0.95
3 | Business case
3.1 | Unclear or unrealistic project proposal and reasons why it should go ahead | More difficult or unlikely to obtain approval to commence the project | 3 | 0.5 | 1.5 | Transfer risk
3.2 | Proposal does not support the business strategy and goals | May still obtain project approval, but less likely | 0 | 0 | 0 | Chose strategy
3.3 | A poor or negative ROI (Return on investment) and a long payback period | Less likely to obtain project approval | 8 | 0.8 | 6.4 | Mitigate risk
3.4 | Unclear or unrealistic cost benefit analysis | Confusion as to what the real financial benefits and costs are, possibly not accepting the analysis and / or leading to extra work to clarify | 1 | 0.1 | 0.1 | Chose strategy
3.5 | Inadequate project implementation budget, or funding commitment for the project | Having to work with a reduced project budget, looking for cost savings, cutting corners, possibly reducing the scope of the project and / or reapplying for each project phase | 3 | 0.6 | 1.8 | Avoid risk
3.6 | No outline project implementation plan or an unclear plan | Unable to explain how the project would be implemented, its phases, key activities and dates, outline resourcing needs, leading to increased concerns | 6 | 0.3 | 1.8 | Mitigate risk
3.7 | Unrealistic, or unmanageable / excessively tight implementation dates | Potentially unable to meet deadlines / key dates, even if extra resources or overtime worked | 3 | 0.3 | 0.9 | Avoid risk
3.8 | Conflict with critical business dates or deadlines | Potential delays on the project (if critical business work takes priority), or possibly an adverse impact on both as staff struggle to deal with both situations | 2 | 0.6 | 1.2 | Avoid risk
3.9 | Outline implementation plans not agreed in principle (by users, IT, project manager and management) | Different implementation ideas / strategies, possible disagreements, delays whilst these are resolved | 1 | 0.1 | 0.1 | Chose strategy
3.1 | Implementation risk assessment either not carried out or significant risks initially identified | Steering group / management wary of proceeding until assessment carried out, or risk responses / recommendations / actions identified to reduce the risks | 2 | 0.4 | 0.8 | Avoid risk
3.11 | Unclear outline system selection project plan, showing how the new system would be selected eg the process, key stages, dates | Increased concerns about the selection process, people knowing what they should be doing and achieving the desired deliverables | 3 | 0.4 | 1.2 | Transfer risk
3.12 | Unrealistic, or excessively tight system selection dates | Potentially unable to meet deadlines / key dates, even if extra resources or overtime worked | 1 | 0.1 | 0.1 | Chose strategy
3.13 | Limited system selection budget | Saving costs wherever possible, reducing the use of external organisations and doing more in-house | 3 | 0.6 | 1.8 | Avoid risk
3.14 | Outline measurable project metrics not yet identified (for either system selection or implementation) | Increased difficulty or inability to measure project progress / achievement of deliverables | 1 | 0.1 | 0.1 | Chose strategy
3.15 | Internal politics influencing the proposal / project | May adversely delay the project, consume time and resources or move the project in unforeseen directions | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 1.1933
4 | Executive support
4.1 | No or uncommitted / unenthusiastic project sponsor | Project unlikely to progress | 3 | 0.3 | 0.9 | Avoid risk
4.2 | Limited project sponsor involvement | Project may lose momentum, especially if trying to resolve issues for which sponsor's input / help is needed | 4 | 0.2 | 0.8 | Avoid risk
4.3 | Project sponsor not having a personal stake in the project ie not personally relying on the new system | Sponsor may have less interest in seeing the project through, eg if the sponsor acquires other work commitments or demands | 1 | 0.1 | 0.1 | Chose strategy
4.4 | Partial or limited executive level support | Potentially difficult project progress, particularly if the project spans a number of departments | 1 | 0.1 | 0.1 | Chose strategy
4.5 | Limited executive level involvement eg not attending steering group meetings, carrying out agreed tasks | Potentially slowing the project, giving out the wrong messages to the project team, users | 1 | 0.1 | 0.1 | Chose strategy
4.6 | Limited or patchy user department management support | Possible lack of time or interest, or potential conflicts with the project - which may slow the project down | 1 | 0.1 | 0.1 | Chose strategy
4.7 | Limited IT department management support | Possible limited interest, or limited resources available for this project | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 0.31429
5 | Scope
5.1 | Project scope not clearly defined or amendable | Difficult to know what the boundaries of project are and / or potentially changing project | 1 | 0.1 | 0.1 | Chose strategy
5.2 | Project size - the larger it is, the greater the complexity - the greater the impact | The more difficult it is to select / implement and achieve the deliverables | 1 | 0.1 | 0.1 | Chose strategy
5.3 | Known solution constraints eg technical, system | The more constraints, the greater the potential adverse impact, reduced options, need to work around the constraints | 3 | 0.4 | 1.2 | Avoid risk
5.4 | Increased need for software customisation | The greater the workload, resources required, time scales | 1 | 0.1 | 0.1 | Chose strategy
5.5 | The need for bespoke coding | The greater the workload, resources required, time scales, impact to software warranty / Service Level Agreement | 1 | 0.1 | 0.1 | Chose strategy
5.6 | System interfaces - the larger the number and greater the complexity, the greater the impact | The greater the workload, resources required, time scales and potentially interface faults that need resolving | 5 | 0.2 | 1 | Mitigate risk
5.7 | Not having a small amount of data to be converted to the new system | Potentially a greater workload, more resources required, longer time scales and possible more mistakes | 1 | 0.1 | 0.1 | Chose strategy
5.8 | Not including sufficient business process re-engineering with the new software in the project | Potentially the new system would operate less efficiently than it could do | 6 | 0.2 | 1.2 | Avoid risk
|  | Average Weighted Score |  |  | 0.4875
6 | Business / project requirements
6.1 | Outline requirements not documented or agreed | Potentially unclear or conflicting requirements, holding back project progress | 3 | 0.7 | 2.1 | Avoid risk
6.2 | Detailed business / project requirements specification not fully documented or agreed | Potentially unclear or conflicting requirements, holding back project progress | 1 | 0.1 | 0.1 | Chose strategy
6.3 | Not all relevant users involved with drawing up the requirements | Remaining users who may have valid contributions to make, may be ignored, to the detriment of the project | 8 | 0.1 | 0.8 | Mitigate risk
6.4 | Inability to agree requirements | Potential disagreements, conflict and difficult to resolve issues | 1 | 0.1 | 0.1 | Chose strategy
6.5 | A high number of changes to the requirements | Extra workload, more time taken, possibly unable to agree the requirements | 1 | 0.1 | 0.1 | Chose strategy
6.6 | No formal change control process for the requirements | Inability to control changes to the requirements | 1 | 0.1 | 0.1 | Chose strategy
6.7 | Project requirements incompatible with existing systems infrastructure | Potentially a high number of changes to either the existing infrastructure or the new systems will be required | 2 | 0.4 | 0.8 | Avoid risk
6.8 | Requirements not formally signed off, despite being agreed | Potentially a disagreement with the requirements | 2 | 0.2 | 0.4 | Transfer risk
|  | Average Weighted Score |  |  | 0.5625
7 | User involvement
7.1 | Users not really involved with the selection process | Users may lack time to be involved, may not be interested, may not want or wish to 'own' the new system | 1 | 0.1 | 0.1 | Chose strategy
7.2 | Users not defining the project / business objectives | IT or another department defining the project / business objectives, who may provide adequate objectives, but items may be missed if the users are not involved | 1 | 0.1 | 0.1 | Chose strategy
7.3 | Difficult for users to be involved with the selection process | Users may lack time to be involved, or management may not support or allow time for the users to be involved, so crucial user input may not be obtained | 7 | 0.2 | 1.4 | Mitigate risk
7.4 | Users not driving the project forward | IT driving the project forward, raising questions as to user desire for the new system | 1 | 0.1 | 0.1 | Chose strategy
7.5 | User(s) not willing to accept changes eg of system and processes | Potential difficulties in moving the project forward and ultimately implementing the best possible solution | 1 | 0.1 | 0.1 | Chose strategy
7.6 | Not all users identified | Will miss input from users not identified, potential gaps in knowledge / requirements | 3 | 0.5 | 1.5 | Avoid risk
7.7 | Irregular or limited communication with users | Users not knowing what is going on or how it will impact them, leading to the growth of speculation and rumours | 2 | 0.4 | 0.8 | Mitigate risk
7.8 | Difficult for user(s) to access the Project Team, Manager, Sponsor | Users struggling to get their input heard / included | 2 | 0.3 | 0.6 | Avoid risk
7.9 | Only a few core users participating within the system selection process | Unless the few core users communicate thoroughly with the remainder of users, potentially items will be missed eg within the new system requirements or other aspects of the system selection | 1 | 0.1 | 0.1 | Chose strategy
7.1 | Users inexperienced or lacking sufficient technical skills in the day-to-day business operations and processes | Potential difficulties in identifying the new system requirements, no clear ideas for the new system or processes, slower progress | 1 | 0.1 | 0.1 | Chose strategy
7.11 | Users inexperienced with system selection process | Users requiring time to learn and understand the process, possibly training or 'hand holding' at many stages | 1 | 0.1 | 0.1 | Chose strategy
7.12 | Users inexperienced with system implementation processes | Users not aware of the potential system implementation problems, the stages or what is required of them in the process | 4 | 0.3 | 1.2 | Avoid risk
7.13 | Limited user experience of different software systems (eg as could be obtained from previously working in different organisations) | Users may lack knowledge of other software systems - what they can or can not do, vendor support, which would be useful when selecting a new system | 1 | 0.1 | 0.1 | Chose strategy
7.14 | Users too busy, with high levels of overtime, just to cope with the existing operational workloads | Users unable to provide sufficient input into the system selection process, possibly requiring additional resources to help with existing workloads | 1 | 0.4 | 0.4 | Avoid risk
|  | Average Weighted Score |  |  | 0.47857
8 | Project manager and IT support
8.1 | Unqualified project manager or inexperienced in the selection process or the software system application | Potentially any lack of experience / knowledge may hamper the selection process | 2 | 0.2 | 0.4 | Chose strategy
8.2 | Project manager too busy with other tasks / existing workload, too little time for this project | Insufficient attention to this project, reliance on others, progress not as good as it could be, mistakes may be made | 1 | 0.1 | 0.1 | Chose strategy
8.3 | IT support staff largely inexperienced with the system selection process | Over reliance on those who have the experience, possible extra training, extra time required to check / manage those with less experience | 3 | 0.6 | 1.8 | Mitigate risk
8.4 | IT support staff largely lacking system selection technical expertise / skills | Over reliance on those who have the technical expertise / skills, urgent need for training | 1 | 0.1 | 0.1 | Chose strategy
8.5 | IT support staff too busy, with high levels of overtime, just to cope with their existing workloads | IT support staff unable to provide sufficient input into the system selection process, possibly requiring additional resources to help with existing workloads | 3 | 0.2 | 0.6 | Accept risk
|  | Average Weighted Score |  |  | 0.6
9 | Software system infrastructure
9.1 | Need to upgrade or replace server(s), PC(s) | Additional costs, work required, scheduling effort | 4 | 0.2 | 0.8 | Avoid risk
9.2 | Need to upgrade to latest database version | Additional costs, work required, scheduling effort | 1 | 0.1 | 0.1 | Chose strategy
9.3 | Change to a different type (and vendor) of database | Additional costs, extra work, scheduling effort, need to learn about and manage the new database | 1 | 0.1 | 0.1 | Chose strategy
9.4 | Network upgrade or complete replacement | Additional costs, work required, scheduling effort | 1 | 0.1 | 0.1 | Chose strategy
9.5 | Selecting an Cloud / on-premise solution | Strategic direction / impact, issues about existing system / staffing | 2 | 0.3 | 0.6 | Mitigate risk
9.6 | Need to upgrade or replace system security | Additional costs, work required, scheduling effort | 1 | 0.1 | 0.1 | Chose strategy
9.7 | Existing system application documentation of variable quality, or missing some or all | Require additional time and effort to understand the existing system application | 1 | 0.1 | 0.1 | Chose strategy
9.8 | Existing system interfaces documentation of variable quality, or missing some or all | Require additional time and effort to understand and document the interfaces | 7 | 0.4 | 2.8 | Avoid risk
9.9 | Existing system processes and workflows documentation of variable quality, or missing some or all | Require additional time and effort to understand and document the workflows / processes | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 0.53333
10 | Project management of the system selection
10.1 | Insufficiently detailed system selection project plan covering the stages, activities, dates, responsibilities, departments, deliverables | Potential confusion, tasks missed, effort duplicated | 1 | 0.1 | 0.1 | Chose strategy
10.2 | Unreliable estimates for the system selection plan tasks | Tasks may take less or much more time, with a knock-on effect to other tasks (especially those on the critical path) and to the overall time scale | 1 | 0.1 | 0.1 | Chose strategy
10.3 | Unrealistic deliverables / milestones | Over scheduling of resources, corners cut | 1 | 0.1 | 0.1 | Chose strategy
10.4 | System selection plan not including any constraints eg training, shut downs, holidays, contingency time | Unrealistic project plan, potentially unable to meet deadlines / deliverables | 1 | 0.1 | 0.1 | Chose strategy
10.5 | System selection plan excludes details project of management tasks eg project meetings, documentation, reporting, communication | Unrealistic project plan, potentially unable to meet deadlines / deliverables | 1 | 0.1 | 0.1 | Chose strategy
10.6 | No ongoing re-evaluation and management of system selection risks. Initial impacts and probabilities may change. New risks may arise. | Will not be aware of changing or new risks, which may adversely affect the project | 1 | 0.1 | 0.1 | Chose strategy
10.7 | No fall back plan(s) in the event of unforeseen occurrences with the system selection | Lack of preparation should such an occurrence happen | 1 | 0.1 | 0.1 | Chose strategy
10.8 | No process of identifying, collecting and reporting system selection costs | Costs not monitored, potential cost overruns | 1 | 0.1 | 0.1 | Chose strategy
10.9 | Project decisions not made by project sponsor, project manager or small team as relevant / when required eg no standard process, or all decisions referred to formal steering group meetings | Inability to progress the project, confusing decisions, or delays awaiting steering group meetings | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 0.1
11 | Vendor and software system information
11.1 | Not identifying all the relevant potential system vendors, prior to issuing an RFI (Request for Information) / short listing | Potentially missing a good solution altogether, or possibly finding a it later in the process (when it may be too late, or require much extra work to do anything about it) | 1 | 0.1 | 0.1 | Chose strategy
11.2 | Not requesting the relevant outline information from a vendor ie not using or only partly using an RFI | May not have all the required information to include or exclude a system / vendor from the short list, extra effort to obtain such information | 1 | 0.1 | 0.1 | Chose strategy
11.3 | Misleading vendor information (accidental or otherwise) | Incorrect analysis, false basis for decisions (depending upon the size of the misleading information) | 1 | 0.1 | 0.1 | Chose strategy
11.4 | Misinterpretation of vendor information by project team | Incorrect analysis, potentially affecting decision for inclusion or exclusion from short list (depending upon size of error) | 1 | 0.1 | 0.1 | Chose strategy
11.5 | Vendors not being authors of the software | Dependent upon another 3rd party (the software author) and consequently having very little input into the future direction / development of the software. May be unable to contact the software authors directly. | 1 | 0.1 | 0.1 | Chose strategy
11.6 | No vendor system demonstrations to confirm outline details, prior to short listing | Unable to directly confirm vendor responses to the RFI by seeing or reviewing the system in action | 1 | 0.1 | 0.1 | Chose strategy
11.7 | Not using demonstration scripts (or at least a list of key questions) that all vendors have to follow when giving their system demonstrations | Much harder to compare the different systems / vendors | 1 | 0.1 | 0.1 | Chose strategy
11.8 | Not short listing the most appropriate vendors for the business needs, possibly due to a number of factors eg not fully reviewing / analysing the options prior to the decision | Potentially creating an inappropriate short list of vendors / software system solutions, with which to proceed with in the detailed selection process | 1 | 0.1 | 0.1 | Chose strategy
11.9 | Not requesting the relevant detailed information from short listed vendors eg not using an RFP (Request for Proposal) | May not have all the required information to assist with the selection process, extra effort to obtain such information | 1 | 0.1 | 0.1 | Chose strategy
11.1 | Not fully reviewing / evaluating the RFP responses and undertaking limited further detailed investigations of the short listed software systems | Potentially missing critical information | 1 | 0.1 | 0.1 | Chose strategy
11.11 | Not undertaking any prototyping | Missing the opportunity to have hands-on experience and test critical areas of the new software solution | 1 | 0.1 | 0.1 | Chose strategy
11.12 | Not having further detailed system demonstrations to assist with investigations | Missing a face-to-face opportunity to resolve and clarify outstanding issues from either RFP responses, prototyping or further investigations | 1 | 0.1 | 0.1 | Chose strategy
11.13 | Limited list of vendor customer references and not properly checking these out | Vendor is not being open in letting a potential new customer choose from any existing customer for a vendor / software reference. And not checking out references properly ie no site visits / telephone calls, may reduce any reassurance for the vendor and its system capabilities. | 1 | 0.1 | 0.1 | Chose strategy
11.14 | Questionable vendor financial stability | Vendor may have future financial difficulties | 1 | 0.1 | 0.1 | Chose strategy
11.15 | Variable quality vendor support, multiple support service levels (SLA's) | Vendor support may be acceptable whilst implementing (but may not when live running / fully operational), inappropriate SLA's | 1 | 0.1 | 0.1 | Chose strategy
11.16 | Vendor does not publish software system upgrade details or development plans | Unsure as to what is included within the upgrades and what the future plans are for the software | 1 | 0.1 | 0.1 | Chose strategy
11.17 | Confusion or lack of clarity of what is included within the vendor's quoted software system price | Possible mistaken inclusion of modules / functionality which may actually be additional extra charges | 1 | 0.1 | 0.1 | Chose strategy
11.18 | No deferred payments tied to system delivery and / or unsatisfactory contract | Payments too early during the system implementation, contract not fair and requiring resolution | 1 | 0.1 | 0.1 | Chose strategy
|  | Average Weighted Score |  |  | 0.1
Memo item:
Chose strategy
Avoid risk
Transfer risk
Mitigate risk
Accept risk